## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : Adhya Radhakrishna
Task Name : Swimming Pool
Page 1 of 1
Total Records: 221 Records 1 to 221
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | Soling Soling 18" | 10 | Started | Material | (M)Rubble | BRASS | 15 | 2100 | 31500 | 0 | 0 | 0 | 2 | 2100 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 27300 | 31500
2 | Soling Soling 18" | 10 | Started | Labour | (L)Soling Only Labour | SQFT | 1248.16 | 16.52 | 20619.6 | 0 | 0 | 0 | 125 | 16.52 | 2065 | 1248.16 | 16.52 | 20619.6 | 1248.16 | 16.52 | 20619.6 | 1123.16 | 0 | 18554.603 | 0.0032
3 | PCC Above Soling Swimming Pool PCC | 10 | Started | Material | (M)RMC M-15 | CUM | 12.5 | 4550 | 56875 | 0 | 0 | 0 | 1 | 4550 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 12.5 | 52325 | 56875
4 | PCC Above Soling Swimming Pool PCC | 10 | Started | Labour | (L)PCC M15 Concrete Only Labour | SQ.FT | 1138.21 | 16.52 | 18803.23 | 0 | 0 | 0 | 114 | 16.52 | 1883.28 | 1138.21 | 16.52 | 18803.22 | 1138.21 | 16.52 | 18803.22 | 1024.21 | 0 | 16919.949 | 0.0092
5 | PCC Above Soling Kids Pool PCC | 10 | Started | Material | (M)RMC M-15 | CUM | 3.5 | 4550 | 15925 | 0 | 0 | 0 | 0 | 4550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 3.5 | 15925 | 15925
6 | Swimming Pool Raft RMC M25 Concrete | 10 | Started | Material | (M)RMC M-25 | CUM | 14.3 | 5000 | 71500 | 0 | 0 | 0 | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3 | 14.3 | 66500 | 71500
7 | Kids Pool Raft RMC M25 Concrete | 10 | Started | Material | (M)RMC M-25 | CUM | 3.07 | 5000 | 15350 | 3.07 | 5000 | 15350 | 0 | 5000 | 0 | 3.07 | 5207.99 | 15988.5265 | 0 | 0 | 0 | 3.07 | 3.07 | 15350 | 15350
8 | Raft Concrete Swimming Pool Raft R/F | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 16.4414 | 74 | 1216.66 | 16.4414 | 74 | 1216.66 | 2 | 74 | 148 | 16.4414 | 74.34 | 1222.2537 | 0 | 0 | 0 | 14.4414 | 16.4414 | 1068.664 | 1216.6636
9 | Raft Concrete Swimming Pool Raft R/F | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 755.206 | 56.64 | 42774.87 | 755.206 | 56.64 | 42774.87 | 76 | 56.64 | 4304.64 | 755.206 | 59.83 | 45180.9542 | 0 | 0 | 0 | 679.206 | 755.206 | 38470.228 | 42774.8678
10 | Raft Concrete Swimming Pool Raft R/F | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 340.884 | 56.64 | 19307.67 | 340.884 | 56.64 | 19307.67 | 34 | 56.64 | 1925.76 | 340.884 | 61.48 | 20956.8666 | 0 | 0 | 0 | 306.884 | 340.884 | 17381.91 | 19307.6698
11 | Waterproofing Above PCC of Swimming Pool Membrane W/P | 10 | Started | Labour | (L)Membrane W/P | SQFT | 825.938 | 88.5 | 73095.51 | 0 | 0 | 0 | 83 | 88.5 | 7345.5 | 825.938 | 88.5 | 73095.51 | 825.938 | 88.5 | 73095.51 | 742.938 | 0 | 65750.013 | 0.003
12 | Waterproofing Above PCC of Kids Pool Membrane W/P | 10 | Started | Labour | (L)Membrane W/P | SQFT | 251.6226 | 88.5 | 22268.6 | 0 | 0 | 0 | 25 | 88.5 | 2212.5 | 251.6226 | 88.5 | 22268.595 | 251.6226 | 88.5 | 22268.6 | 226.6226 | 0 | 20056.1 | 0.0001
13 | W/P Above Raft Brickbat W/P for Swimming Pool | 10 | Started | Material | (M)Conplast WL Xtra Chemical | KG | 7.7006 | 200 | 1540.12 | 0 | 0 | 0 | 1 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7006 | 7.7006 | 1340.12 | 1540.12
14 | W/P Above Raft Brickbat W/P for Swimming Pool | 10 | Started | Material | (M)M Sand | CUM | 10 | 2226.14 | 22261.4 | 10 | 2226.14 | 22261.4 | 1 | 2226.14 | 2226.14 | 10 | 2226.16 | 22261.571 | 0 | 0 | 0 | 9 | 10 | 20035.26 | 22261.4
15 | W/P Above Raft Brickbat W/P for Swimming Pool | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 8.3 | 320 | 2656 | 8.3 | 320 | 2656 | 1 | 320 | 320 | 8.3 | 270 | 2241.0266 | 0 | 0 | 0 | 7.3 | 8.3 | 2336 | 2656
16 | W/P Above Raft Brickbat W/P for Swimming Pool | 10 | Started | Material | (M)Red Bricks 4" | NOS | 3000.0158 | 8.4 | 25200.13 | 3000 | 8.4 | 25200 | 300 | 8.4 | 2520 | 3000 | 9.52 | 28560 | 0 | 0 | 0 | 2700.0158 | 3000.0158 | 22680.133 | 25200.1327
17 | W/P Of Swimming Pool Pardi W/P Inside Of Pardi | 10 | Started | Material | (M)M Sand | CUM | 4 | 2226.14 | 8904.56 | 4 | 2226.14 | 8904.56 | 0 | 2226.14 | 0 | 4 | 2226.16 | 8904.6284 | 0 | 0 | 0 | 4 | 4 | 8904.56 | 8904.56
18 | W/P Of Swimming Pool Pardi W/P Inside Of Pardi | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 6.72 | 320 | 2150.4 | 6.72 | 320 | 2150.4 | 1 | 320 | 320 | 6.72 | 270 | 1814.4215 | 0 | 0 | 0 | 5.72 | 6.72 | 1830.4 | 2150.4
19 | W/P Of Swimming Pool Pardi W/P Outside Of Pardi | 10 | Started | Material | (M)M Sand | CUM | 2.98 | 2226.14 | 6633.9 | 2.98 | 2226.14 | 6633.9 | 0 | 2226.14 | 0 | 2.98 | 2226.16 | 6633.9482 | 0 | 0 | 0 | 2.98 | 2.98 | 6633.897 | 6633.8972
20 | W/P Of Swimming Pool Pardi W/P Outside Of Pardi | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 9 | 320 | 2880 | 9 | 320 | 2880 | 1 | 320 | 320 | 9 | 270 | 2430.0288 | 0 | 0 | 0 | 8 | 9 | 2560 | 2880
21 | W/P of Changing Room Slab Changing Room W/P | 10 | Started | Material | (M)Red Bricks 4" | NOS | 50 | 8.4 | 420 | 0 | 0 | 0 | 5 | 8.4 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 378 | 420
22 | W/P of Changing Room Slab Changing Room W/P | 10 | Started | Material | (M)URP Dr.Fixit | LITRE | 1 | 360 | 360 | 1 | 360 | 360 | 0 | 360 | 0 | 1 | 360 | 360 | 0 | 0 | 0 | 1 | 1 | 360 | 360
23 | Waterproofing Membrane W/P | 0 | Started | Labour | (L)Membrane W/P | SQFT | 2253.0874 | 88.5 | 199398.23 | 0 | 0 | 0 | 0 | 88.5 | 0 | 2253.0874 | 88.5 | 199398.235 | 2253.0874 | 88.5 | 199398.24 | 2253.0874 | 0 | 199398.235 | -0.0051
24 | Swimming Pool Pardi RMC M25 Concrete | 10 | Started | Material | (M)RMC M-25 | CUM | 7 | 5000 | 35000 | 7 | 5000 | 35000 | 1 | 5000 | 5000 | 7 | 5207.99 | 36455.9237 | 0 | 0 | 0 | 6 | 7 | 30000 | 35000
25 | Kids Pool Pardi RMC M25 Concrete | 10 | Started | Material | (M)RMC M-25 | CUM | 2.5 | 5000 | 12500 | 2.5 | 5000 | 12500 | 0 | 5000 | 0 | 2.5 | 5207.99 | 13019.9728 | 0 | 0 | 0 | 2.5 | 2.5 | 12500 | 12500
26 | Swimming Pool Pardi Swimming Pool Pardi R/F | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 10.68 | 74 | 790.32 | 10.68 | 74 | 790.32 | 1 | 74 | 74 | 10.68 | 74.34 | 793.9512 | 0 | 0 | 0 | 9.68 | 10.68 | 716.32 | 790.32
27 | Swimming Pool Pardi Swimming Pool Pardi R/F | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 712 | 56.64 | 40327.68 | 712 | 56.64 | 40327.68 | 71 | 56.64 | 4021.44 | 712 | 56.29 | 40075.632 | 0 | 0 | 0 | 641 | 712 | 36306.24 | 40327.68
28 | Swimming Pool Drain RMC M25 Concrete | 10 | Started | Material | (M)RMC M-25 | CUM | 2 | 5000 | 10000 | 2 | 5000 | 10000 | 0 | 5000 | 0 | 2 | 5207.99 | 10415.9782 | 0 | 0 | 0 | 2 | 2 | 10000 | 10000
29 | Swimming Pool Drain R/F | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 4.113 | 74 | 304.36 | 4.113 | 74 | 304.36 | 0 | 74 | 0 | 4.113 | 74.34 | 305.7604 | 0 | 0 | 0 | 4.113 | 4.113 | 304.362 | 304.362
30 | Swimming Pool Drain R/F | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 274.2 | 56.64 | 15530.69 | 274.2 | 56.64 | 15530.69 | 27 | 56.64 | 1529.28 | 274.2 | 58.29 | 15983.6664 | 0 | 0 | 0 | 247.2 | 274.2 | 14001.408 | 15530.688
31 | Swimming Pool Pardi Internal Plaster | 10 | Started | Material | (M)M Sand | CUM | 3 | 2226.14 | 6678.42 | 3 | 2226.14 | 6678.42 | 0 | 2226.14 | 0 | 3 | 2226.15 | 6678.4443 | 0 | 0 | 0 | 3 | 3 | 6678.42 | 6678.42
32 | Swimming Pool Pardi Internal Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 43.785 | 320 | 14011.2 | 43.785 | 320 | 14011.2 | 4 | 320 | 1280 | 43.785 | 270 | 11822.0901 | 0 | 0 | 0 | 39.785 | 43.785 | 12731.2 | 14011.2
33 | Swimming Pool Pardi Internal Plaster | 10 | Started | Labour | (L)Internal Plaster Labour | SQFT | 646.246 | 31.67 | 20466.61 | 0 | 0 | 0 | 65 | 31.67 | 2058.55 | 646.246 | 35.4 | 22877.1 | 646.246 | 35.4 | 22877.1 | 581.246 | 0 | 18408.061 | -2410.4892
34 | Swimming Pool Pardi External Plaster | 10 | Started | Material | (M)M Sand | CUM | 2 | 2226.14 | 4452.28 | 2 | 2226.14 | 4452.28 | 0 | 2226.14 | 0 | 2 | 2226.15 | 4452.2962 | 0 | 0 | 0 | 2 | 2 | 4452.28 | 4452.28
35 | Swimming Pool Pardi External Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 6 | 320 | 1920 | 6 | 320 | 1920 | 1 | 320 | 320 | 6 | 270 | 1620.0192 | 0 | 0 | 0 | 5 | 6 | 1600 | 1920
36 | Swimming Pool Pardi External Plaster | 10 | Started | Labour | (L)External Plaster Labour | SQFT | 265.254 | 31.67 | 8400.59 | 0 | 0 | 0 | 27 | 31.67 | 855.09 | 265.254 | 35.4 | 9390 | 265.254 | 35.4 | 9390 | 238.254 | 0 | 7545.504 | -989.4058
37 | Plastering Brickwork, Shower Wall, Sitting Plaster | 10 | Started | Material | (M)M Sand | CUM | 2.8303 | 2226.14 | 6300.64 | 2.8303 | 2226.14 | 6300.64 | 0 | 2226.14 | 0 | 2.8303 | 2226.15 | 6300.667 | 0 | 0 | 0 | 2.8303 | 2.8303 | 6300.644 | 6300.644
38 | Plastering Brickwork, Shower Wall, Sitting Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 28.3026 | 320 | 9056.83 | 28.3026 | 320 | 9056.83 | 3 | 320 | 960 | 28.3026 | 270 | 7641.7926 | 0 | 0 | 0 | 25.3026 | 28.3026 | 8096.832 | 9056.832
39 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 6" B | 10 | Started | Material | (M)Flyash Bricks 5" | NOS | 2194 | 11 | 24134 | 2194 | 11 | 24134 | 219 | 11 | 2409 | 2194 | 8.96 | 19658.24 | 0 | 0 | 0 | 1975 | 2194 | 21725 | 24134
40 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 6" B | 10 | Started | Material | (M)Flyash Bricks 6" | NOS | 2257.9957 | 10.08 | 22760.6 | 63 | 10.08 | 635.04 | 226 | 10.08 | 2278.08 | 63 | 10.08 | 635.04 | 0 | 0 | 0 | 2031.9957 | 2257.9957 | 20482.517 | 22760.5967
41 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 6" B | 10 | Started | Material | (M)M Sand | CUM | 5 | 2226.14 | 11130.7 | 5 | 2226.14 | 11130.7 | 1 | 2226.14 | 2226.14 | 5 | 2226.15 | 11130.7405 | 0 | 0 | 0 | 4 | 5 | 8904.56 | 11130.7
42 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 6" B | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 13.9998 | 320 | 4479.94 | 13.9998 | 320 | 4479.94 | 1 | 320 | 320 | 13.9998 | 270 | 3779.9908 | 0 | 0 | 0 | 12.9998 | 13.9998 | 4159.936 | 4479.936
43 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 6" B | 10 | Started | Labour | (L)6" Brickwork Only Labour | SQ.FT | 601.71 | 28.32 | 17040.43 | 0 | 0 | 0 | 60 | 28.32 | 1699.2 | 601.71 | 28.32 | 17040.42 | 601.71 | 28.32 | 17040.42 | 541.71 | 0 | 15341.227 | 0.0072
44 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 9" B | 10 | Started | Material | (M)Flyash Bricks 5" | NOS | 1000 | 11 | 11000 | 1000 | 11 | 11000 | 100 | 11 | 1100 | 1000 | 8.96 | 8960 | 0 | 0 | 0 | 900 | 1000 | 9900 | 11000
45 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 9" B | 10 | Started | Material | (M)Flyash Bricks 6" | NOS | 1177 | 10.08 | 11864.16 | 1177 | 10.08 | 11864.16 | 118 | 10.08 | 1189.44 | 1177 | 10.08 | 11864.16 | 0 | 0 | 0 | 1059 | 1177 | 10674.72 | 11864.16
46 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 9" B | 10 | Started | Material | (M)M Sand | CUM | 5 | 2226.14 | 11130.7 | 5 | 2226.14 | 11130.7 | 1 | 2226.14 | 2226.14 | 5 | 2226.15 | 11130.7405 | 0 | 0 | 0 | 4 | 5 | 8904.56 | 11130.7
47 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 9" B | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 5.4409 | 320 | 1741.09 | 5.4409 | 320 | 1741.09 | 1 | 320 | 320 | 5.4409 | 270 | 1469.0604 | 0 | 0 | 0 | 4.4409 | 5.4409 | 1421.088 | 1741.088
48 | Flowerbed, Shower Wall, Sitting Under Pergola Brickwork 9" B | 10 | Started | Labour | (L)9" Brickwork only Labour | SQFT | 284.76 | 31.86 | 9072.45 | 0 | 0 | 0 | 28 | 31.86 | 892.08 | 284.76 | 31.86 | 9072.46 | 284.76 | 31.86 | 9072.46 | 256.76 | 0 | 8180.374 | -0.0064
49 | Backfilling in Deck | 10 | Started | Material | (M)Murum | CUM | 56.6 | 333.94 | 18901 | 56.6 | 333.94 | 18901 | 6 | 333.94 | 2003.64 | 40 | 241.17 | 9646.64 | 0 | 0 | 0 | 50.6 | 56.6 | 16897.364 | 18901.004
50 | Changing Room 9" Brickwork Below Ground | 10 | Started | Material | (M)Flyash Bricks 6" | NOS | 2260.0737 | 10.08 | 22781.54 | 2260 | 10.08 | 22780.8 | 226 | 10.08 | 2278.08 | 2260 | 10.08 | 22780.8 | 0 | 0 | 0 | 2034.0737 | 2260.0737 | 20503.463 | 22781.5429
51 | Changing Room 9" Brickwork Below Ground | 10 | Started | Material | (M)M Sand | CUM | 2 | 2226.14 | 4452.28 | 2 | 2226.14 | 4452.28 | 0 | 2226.14 | 0 | 2 | 2226.15 | 4452.2962 | 0 | 0 | 0 | 2 | 2 | 4452.28 | 4452.28
52 | Changing Room 9" Brickwork Below Ground | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 5.6485 | 320 | 1807.52 | 5.6485 | 320 | 1807.52 | 1 | 320 | 320 | 5.6485 | 270 | 1525.1131 | 0 | 0 | 0 | 4.6485 | 5.6485 | 1487.52 | 1807.52
53 | Changing Room 6" Brickwork Flower Bed | 10 | Started | Material | (M)Flyash Bricks 5" | NOS | 1000 | 11 | 11000 | 1000 | 11 | 11000 | 100 | 11 | 1100 | 1000 | 8.96 | 8960 | 0 | 0 | 0 | 900 | 1000 | 9900 | 11000
54 | Changing Room 6" Brickwork Flower Bed | 10 | Started | Material | (M)Flyash Bricks 6" | NOS | 1337.8576 | 10.08 | 13485.6 | 0 | 0 | 0 | 134 | 10.08 | 1350.72 | 0 | 0 | 0 | 0 | 0 | 0 | 1203.8576 | 1337.8576 | 12134.885 | 13485.6046
55 | Changing Room 6" Brickwork Flower Bed | 10 | Started | Material | (M)M Sand | CUM | 2.741 | 2226.14 | 6101.85 | 2.741 | 2226.14 | 6101.85 | 0 | 2226.14 | 0 | 2.741 | 2226.15 | 6101.8719 | 0 | 0 | 0 | 2.741 | 2.741 | 6101.85 | 6101.8497
56 | Changing Room 6" Brickwork Flower Bed | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 8.2948 | 320 | 2654.34 | 8.2948 | 320 | 2654.34 | 1 | 320 | 320 | 8.2948 | 270 | 2239.6225 | 0 | 0 | 0 | 7.2948 | 8.2948 | 2334.336 | 2654.336
57 | Changing Room Internal Tar Plaster | 10 | Started | Material | (M)M Sand | CUM | 1.5 | 2226.14 | 3339.21 | 1.5 | 2226.14 | 3339.21 | 0 | 2226.14 | 0 | 1.5 | 2226.15 | 3339.2222 | 0 | 0 | 0 | 1.5 | 1.5 | 3339.21 | 3339.21
58 | Changing Room Internal Tar Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 5.28 | 320 | 1689.6 | 5.28 | 320 | 1689.6 | 1 | 320 | 320 | 5.28 | 270 | 1425.6169 | 0 | 0 | 0 | 4.28 | 5.28 | 1369.6 | 1689.6
59 | Changing Room Internal Ceiling Plaster | 10 | Started | Material | (M)M Sand | CUM | 1 | 2226.14 | 2226.14 | 1 | 2226.14 | 2226.14 | 0 | 2226.14 | 0 | 1 | 2226.15 | 2226.1481 | 0 | 0 | 0 | 1 | 1 | 2226.14 | 2226.14
60 | Changing Room Internal Ceiling Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 1 | 320 | 320 | 1 | 320 | 320 | 0 | 320 | 0 | 1 | 270 | 270.0032 | 0 | 0 | 0 | 1 | 1 | 320 | 320
61 | Changing Room Internal Ceiling Plaster | 10 | Started | Material | (M)Sanala (25kg per bag) | BAG | 0.4 | 141.6 | 56.64 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 56.64 | 56.64
62 | Changing Room External Plaster | 10 | Started | Material | (M)M Sand | CUM | 2.5 | 2226.14 | 5565.35 | 2.5 | 2226.14 | 5565.35 | 0 | 2226.14 | 0 | 2.5 | 2226.15 | 5565.3703 | 0 | 0 | 0 | 2.5 | 2.5 | 5565.35 | 5565.35
63 | Changing Room External Plaster | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 7.9905 | 320 | 2556.96 | 7.9905 | 320 | 2556.96 | 1 | 320 | 320 | 7.9905 | 270 | 2157.4606 | 0 | 0 | 0 | 6.9905 | 7.9905 | 2236.96 | 2556.96
64 | Changing Room Flooring | 11.11 | Started | Material | (M)1256-Floor | SQM | 5.04 | 283.96 | 1431.16 | 5.04 | 283.96 | 1431.16 | 1 | 283.96 | 283.96 | 5.04 | 338.72 | 1707.1669 | 0 | 0 | 0 | 4.04 | 5.04 | 1147.198 | 1431.1584
65 | Changing Room Changing Room Wall Tiles | 9.15 | Started | Material | (M)1256-HL | SQM | 23.49 | 283.96 | 6670.22 | 23.49 | 283.96 | 6670.22 | 2 | 283.96 | 567.92 | 23.49 | 301.27 | 7076.8462 | 0 | 0 | 0 | 21.49 | 23.49 | 6102.3 | 6670.2204
66 | Changing Room Slab | 10 | Started | Material | (M)RMC M-15 | CUM | 0.776 | 4550 | 3530.8 | 0.489 | 4550 | 2224.95 | 0 | 4550 | 0 | 0.489 | 4000 | 1956 | 0 | 0 | 0 | 0.776 | 0.776 | 3530.8 | 3530.8
67 | Changing Room Slab | 10 | Started | Labour | (L)Changing room Slab labours | lumsum | 1 | 8850 | 8850 | 0 | 0 | 0 | 0 | 8850 | 0 | 1 | 8850 | 8850 | 1 | 8850 | 8850 | 1 | 0 | 8850 | 0
68 | Tiling Granite For Swimming Pool | 9.55 | Started | Material | (M)Araldite | KG | 1 | 849.6 | 849.6 | 1 | 849.6 | 849.6 | 0 | 849.6 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 849.6 | 849.6
69 | Tiling Granite For Swimming Pool | 9.55 | Started | Material | (M)Cofee Brown Granite | SQM | 32 | 1650.58 | 52818.56 | 32 | 1650.58 | 52818.56 | 3 | 1650.58 | 4951.74 | 31.6472 | 1733.27 | 54853.0759 | 0 | 0 | 0 | 29 | 32 | 47866.82 | 52818.56
70 | Tiling Granite For Swimming Pool | 9.55 | Started | Labour | (L)Granite Cutting & Fixing Labours only | RFT | 444 | 82.6 | 36674.4 | 0 | 0 | 0 | 42 | 82.6 | 3469.2 | 444 | 82.6 | 36674.4 | 444 | 82.6 | 36674.4 | 402 | 0 | 33205.2 | 0
71 | Tiling Granite For Swimming Pool | 9.55 | Started | Labour | (L)Granite moulding Labours only | RFT | 251 | 47.2 | 11847.2 | 0 | 0 | 0 | 24 | 47.2 | 1132.8 | 251 | 47.2 | 11847.2 | 251 | 47.2 | 11847.2 | 227 | 0 | 10714.4 | 0
72 | Tiling Granite For Swimming Pool | 9.55 | Started | Labour | (L)Granite Polish | RFT | 155 | 23.6 | 3658 | 0 | 0 | 0 | 15 | 23.6 | 354 | 155 | 23.6 | 3658 | 155 | 23.6 | 3658 | 140 | 0 | 3304 | 0
73 | Tiling Artificial Lawn | 10 | Started | Material | (M)Artificial Lawn 40mm Thk | SQM | 2.6 | 226.56 | 589.06 | 0 | 0 | 0 | 0 | 226.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 589.056 | 589.056
74 | Tiling Deck Tiles | 9.2 | Started | Material | (M)Acid | LITRE | 7 | 47.2 | 330.4 | 7 | 47.2 | 330.4 | 1 | 47.2 | 47.2 | 7 | 47.2 | 330.4 | 0 | 0 | 0 | 6 | 7 | 283.2 | 330.4
75 | Tiling Deck Tiles | 9.2 | Started | Material | (M)Grout | KG | 2 | 94.4 | 188.8 | 2 | 94.4 | 188.8 | 0 | 94.4 | 0 | 2 | 94.4 | 188.8 | 0 | 0 | 0 | 2 | 2 | 188.8 | 188.8
76 | Tiling Deck Tiles | 9.2 | Started | Material | (M)Wooden Finish Deck Tiles | SQM | 47.52 | 166.98 | 7934.89 | 47.52 | 166.98 | 7934.89 | 4 | 166.98 | 667.92 | 47.52 | 560.49 | 26634.7034 | 0 | 0 | 0 | 43.52 | 47.52 | 7266.97 | 7934.8896
77 | Tiling Grating for Gutter | 10 | Started | Material | (M)MS Grating | SQM | 3.51 | 1.18 | 4.14 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 3.51 | 4.142 | 4.1418
78 | Tiling Open Shower Wall Tiles | 9.26 | Started | Material | (M)Esatilo Negro | SQM | 7.56 | 233.76 | 1767.23 | 7.56 | 233.76 | 1767.23 | 1 | 233.76 | 233.76 | 7.56 | 840.08 | 6351.0373 | 0 | 0 | 0 | 6.56 | 7.56 | 1533.466 | 1767.2256
79 | Tiling Open Shower Tiles | 10 | Started | Material | (M)Black Pebbles | KG | 33 | 80 | 2640 | 33 | 80 | 2640 | 3 | 80 | 240 | 33 | 80 | 2640 | 0 | 0 | 0 | 30 | 33 | 2400 | 2640
80 | Tiling Open Shower Tiles | 10 | Started | Material | (M)White Cement | KG | 50 | 59 | 2950 | 50 | 59 | 2950 | 5 | 59 | 295 | 50 | 35.4 | 1770 | 0 | 0 | 0 | 45 | 50 | 2655 | 2950
81 | Tiling Drain Tiles | 10 | Started | Material | (M)1256-LT | SQM | 7.29 | 283.96 | 2070.07 | 7.29 | 283.96 | 2070.07 | 1 | 283.96 | 283.96 | 7.29 | 312.28 | 2276.5543 | 0 | 0 | 0 | 6.29 | 7.29 | 1786.108 | 2070.0684
82 | Tiling Swimming Pool Tiling | 0 | Started | Labour | (L)Piccolo Mosaic Tile Fixing Labours | SQFT | 1054 | 194.7 | 205213.8 | 0 | 0 | 0 | 0 | 194.7 | 0 | 1054 | 194.7 | 205213.8 | 1054 | 194.7 | 205213.8 | 1054 | 0 | 205213.8 | 0
83 | Tiling Swimming Pool Tiling | 0 | Started | Labour | (L)Piccolo Mosaic Tiles | SQFT | 1054 | 167.56 | 176608.24 | 0 | 0 | 0 | 0 | 167.56 | 0 | 1054 | 167.56 | 176608.24 | 1054 | 167.56 | 176608.24 | 1054 | 0 | 176608.24 | 0
84 | Deck, Changing room, Shower Wall tile fixing labours only | 0 | Started | Labour | (L)Tile fixing labours only | SQFT | 899 | 41.3 | 37128.7 | 0 | 0 | 0 | 0 | 41.3 | 0 | 899 | 41.3 | 37128.7 | 899 | 41.3 | 37128.7 | 899 | 0 | 37128.7 | 0
85 | Tiling Paving Block fixing Labours only | 0 | Started | Labour | (L)Paving Block Fixing | SQFT | 451 | 17.7 | 7982.7 | 0 | 0 | 0 | 0 | 17.7 | 0 | 451 | 17.7 | 7982.7 | 451 | 17.7 | 7982.7 | 451 | 0 | 7982.7 | 0
86 | PCC Above Backfilling in Deck Area RMC M15 Concrete | 10 | Started | Material | (M)RMC M-15 | CUM | 5.511 | 4550 | 25075.05 | 5.511 | 4550 | 25075.05 | 1 | 4550 | 4550 | 5.511 | 4000 | 22044 | 0 | 0 | 0 | 4.511 | 5.511 | 20525.05 | 25075.05
87 | Pump Room 6" Brickwork | 10 | Started | Material | (M)Flyash Bricks 5" | NOS | 1500 | 11 | 16500 | 1500 | 11 | 16500 | 150 | 11 | 1650 | 1500 | 8.96 | 13440 | 0 | 0 | 0 | 1350 | 1500 | 14850 | 16500
88 | Pump Room 6" Brickwork | 10 | Started | Material | (M)M Sand | CUM | 3.5 | 2226.14 | 7791.49 | 3.5 | 2226.14 | 7791.49 | 0 | 2226.14 | 0 | 3.5 | 2226.15 | 7791.5184 | 0 | 0 | 0 | 3.5 | 3.5 | 7791.49 | 7791.49
89 | Pump Room 6" Brickwork | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 9.548 | 320 | 3055.36 | 9.548 | 320 | 3055.36 | 1 | 320 | 320 | 9.548 | 270 | 2577.9906 | 0 | 0 | 0 | 8.548 | 9.548 | 2735.36 | 3055.36
90 | Pump Room Plastering | 10 | Started | Material | (M)M Sand | CUM | 1.134 | 2226.14 | 2524.44 | 1.134 | 2226.14 | 2524.44 | 0 | 2226.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.134 | 1.134 | 2524.443 | 2524.4428
91 | Pump Room Plastering | 10 | Started | Material | (M)PPC Cement - 50 KGS per Bag | BAG | 11.34 | 320 | 3628.8 | 11.34 | 320 | 3628.8 | 1 | 320 | 320 | 11.34 | 270 | 3061.8363 | 0 | 0 | 0 | 10.34 | 11.34 | 3308.8 | 3628.8
92 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)1" Hanging Clamp | NOS | 25 | 13.92 | 348 | 25 | 13.92 | 348 | 3 | 13.92 | 41.76 | 25 | 10.87 | 271.82 | 0 | 0 | 0 | 22 | 25 | 306.24 | 348
93 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)1" UPVC Elbow | NOS | 6 | 25 | 150 | 6 | 25 | 150 | 1 | 25 | 25 | 6 | 20.19 | 121.1598 | 0 | 0 | 0 | 5 | 6 | 125 | 150
94 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)1" UPVC Socket | NOS | 15 | 25.38 | 380.7 | 15 | 25.38 | 380.7 | 2 | 25.38 | 50.76 | 15 | 13.38 | 200.7397 | 0 | 0 | 0 | 13 | 15 | 329.94 | 380.7
95 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)1"x3/4" UPVC Socket | NOS | 2 | 43.66 | 87.32 | 2 | 43.66 | 87.32 | 0 | 43.66 | 0 | 2 | 18.18 | 36.36 | 0 | 0 | 0 | 2 | 2 | 87.32 | 87.32
96 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)10mm Bullet Fastner | NOS | 25 | 11.8 | 295 | 25 | 11.8 | 295 | 3 | 11.8 | 35.4 | 25 | 9.21 | 230.26 | 0 | 0 | 0 | 22 | 25 | 259.6 | 295
97 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)10mm x 2m long tie rod | NOS | 6 | 182.9 | 1097.4 | 6 | 182.9 | 1097.4 | 1 | 182.9 | 182.9 | 6 | 142.8 | 856.7802 | 0 | 0 | 0 | 5 | 6 | 914.5 | 1097.4
98 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)118ml upvc solvent | NOS | 1 | 207.68 | 207.68 | 1 | 207.68 | 207.68 | 0 | 207.68 | 0 | 1 | 129.71 | 129.71 | 0 | 0 | 0 | 1 | 1 | 207.68 | 207.68
99 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)2" UPVC Socket | NOS | 2 | 93.22 | 186.44 | 2 | 93.22 | 186.44 | 0 | 93.22 | 0 | 2 | 36.87 | 73.74 | 0 | 0 | 0 | 2 | 2 | 186.44 | 186.44
100 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)4" Cutting Wheel | PCS | 4 | 17.7 | 70.8 | 4 | 17.7 | 70.8 | 0 | 17.7 | 0 | 4 | 17.7 | 70.8 | 0 | 0 | 0 | 4 | 4 | 70.8 | 70.8
101 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Brass Angle Cock | NOS | 2 | 411.82 | 823.64 | 2 | 411.82 | 823.64 | 0 | 411.82 | 0 | 2 | 278.65 | 557.3 | 0 | 0 | 0 | 2 | 2 | 823.64 | 823.64
102 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Brass Elbow 3/4"x1/2" | NOS | 8 | 120.36 | 962.88 | 8 | 120.36 | 962.88 | 1 | 120.36 | 120.36 | 8 | 58.41 | 467.28 | 0 | 0 | 0 | 7 | 8 | 842.52 | 962.88
103 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Brass MTA 3/4" | NOS | 6 | 265.5 | 1593 | 6 | 265.5 | 1593 | 1 | 265.5 | 265.5 | 6 | 127.44 | 764.64 | 0 | 0 | 0 | 5 | 6 | 1327.5 | 1593
104 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Brass MTA 3/4"x1/2" | NOS | 6 | 213.58 | 1281.48 | 6 | 213.58 | 1281.48 | 1 | 213.58 | 213.58 | 6 | 106.79 | 640.74 | 0 | 0 | 0 | 5 | 6 | 1067.9 | 1281.48
105 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Concealed Stopcock 3/4" | NOS | 3 | 1600.08 | 4800.24 | 3 | 1600.08 | 4800.24 | 0 | 1600.08 | 0 | 3 | 960.05 | 2880.1401 | 0 | 0 | 0 | 3 | 3 | 4800.24 | 4800.24
106 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Concealed valve 20mm | NOS | 3 | 1436.06 | 4308.18 | 3 | 1436.06 | 4308.18 | 0 | 1436.06 | 0 | 3 | 861.63 | 2584.8999 | 0 | 0 | 0 | 3 | 3 | 4308.18 | 4308.18
107 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Elbow 3/4" | NOS | 20 | 1 | 20 | 20 | 1 | 20 | 2 | 1 | 2 | 20 | 15.33 | 306.56 | 0 | 0 | 0 | 18 | 20 | 18 | 20
108 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Pipe 3/4"X3m long (SDR-11) | NOS | 4 | 281.44 | 1125.76 | 4 | 281.44 | 1125.76 | 0 | 281.44 | 0 | 4 | 270.14 | 1080.54 | 0 | 0 | 0 | 4 | 4 | 1125.76 | 1125.76
109 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Socket 3/4" | NOS | 4 | 28.32 | 113.28 | 4 | 28.32 | 113.28 | 0 | 28.32 | 0 | 4 | 13.31 | 53.24 | 0 | 0 | 0 | 4 | 4 | 113.28 | 113.28
110 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Solvent 237ml | NOS | 2 | 329.92 | 659.84 | 2 | 329.92 | 659.84 | 0 | 329.92 | 0 | 2 | 329.92 | 659.84 | 0 | 0 | 0 | 2 | 2 | 659.84 | 659.84
111 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Step Over Bend 1/2" | NOS | 10 | 31.55 | 315.5 | 10 | 31.55 | 315.5 | 1 | 31.55 | 31.55 | 10 | 67.97 | 679.68 | 0 | 0 | 0 | 9 | 10 | 283.95 | 315.5
112 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC stepover Bend | NOS | 8 | 152.22 | 1217.76 | 8 | 152.22 | 1217.76 | 1 | 152.22 | 152.22 | 8 | 73.46 | 587.64 | 0 | 0 | 0 | 7 | 8 | 1065.54 | 1217.76
113 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Tee 3/4" | NOS | 6 | 1 | 6 | 6 | 1 | 6 | 1 | 1 | 1 | 6 | 25.76 | 154.56 | 0 | 0 | 0 | 5 | 6 | 5 | 6
114 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC Transition Bushing 3/4" | NOS | 1 | 13.02 | 13.02 | 1 | 13.02 | 13.02 | 0 | 13.02 | 0 | 1 | 13.55 | 13.55 | 0 | 0 | 0 | 1 | 1 | 13.02 | 13.02
115 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)CPVC/UPVC Plug 1/2" | NOS | 6 | 7.08 | 42.48 | 6 | 7.08 | 42.48 | 1 | 7.08 | 7.08 | 6 | 7.08 | 42.48 | 0 | 0 | 0 | 5 | 6 | 35.4 | 42.48
116 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Fastner 12 mm X 4" long | PCS | 8 | 29.5 | 236 | 8 | 29.5 | 236 | 1 | 29.5 | 29.5 | 8 | 29.5 | 236 | 0 | 0 | 0 | 7 | 8 | 206.5 | 236
117 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Fevi quick | NOS | 1 | 80 | 80 | 1 | 80 | 80 | 0 | 80 | 0 | 1 | 70.8 | 70.8 | 0 | 0 | 0 | 1 | 1 | 80 | 80
118 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)GI Clip 4" | NOS | 37 | 1 | 37 | 37 | 1 | 37 | 4 | 1 | 4 | 37 | 11.8 | 436.6 | 0 | 0 | 0 | 33 | 37 | 33 | 37
119 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Nahani Trap W/O jali 75mm | NOS | 8 | 68.22 | 545.76 | 8 | 68.22 | 545.76 | 1 | 68.22 | 68.22 | 8 | 78.25 | 626.02 | 0 | 0 | 0 | 7 | 8 | 477.54 | 545.76
120 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Nut Bolt | KG | 0.25 | 141.6 | 35.4 | 0.25 | 141.6 | 35.4 | 0 | 141.6 | 0 | 0.25 | 141.6 | 35.4 | 0 | 0 | 0 | 0.25 | 0.25 | 35.4 | 35.4
121 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Plumbing Nails | KG | 1.5 | 118 | 177 | 1.5 | 118 | 177 | 0 | 118 | 0 | 1.5 | 118 | 177 | 0 | 0 | 0 | 1.5 | 1.5 | 177 | 177
122 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Plumbing Nails 2" | KG | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 106.2 | 106.2 | 0 | 0 | 0 | 1 | 1 | 1 | 1
123 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)PVC Clip 75mm | NOS | 8 | 30.68 | 245.44 | 8 | 30.68 | 245.44 | 1 | 30.68 | 30.68 | 8 | 12.27 | 98.18 | 0 | 0 | 0 | 7 | 8 | 214.76 | 245.44
124 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Shower with Arm | NOS | 3 | 885 | 2655 | 3 | 885 | 2655 | 0 | 885 | 0 | 3 | 798.33 | 2394.9849 | 0 | 0 | 0 | 3 | 3 | 2655 | 2655
125 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Pipes 'A' type S/F 3ft long D/S 75mm | NOS | 1 | 306.98 | 306.98 | 1 | 306.98 | 306.98 | 0 | 306.98 | 0 | 1 | 306.98 | 306.98 | 0 | 0 | 0 | 1 | 1 | 306.98 | 306.98
126 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Pipes 'A' type S/F 6ft long D/S 75mm | NOS | 1 | 232.5 | 232.5 | 1 | 232.5 | 232.5 | 0 | 232.5 | 0 | 1 | 232.5 | 232.5 | 0 | 0 | 0 | 1 | 1 | 232.5 | 232.5
127 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Pipes 'A' type S/s 75mm | NOS | 8 | 808.3 | 6466.4 | 8 | 808.3 | 6466.4 | 1 | 808.3 | 808.3 | 8 | 325.04 | 2600.28 | 0 | 0 | 0 | 7 | 8 | 5658.1 | 6466.4
128 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Pipes 'B' type 6ft long D/S 75mm | NOS | 1 | 217.12 | 217.12 | 1 | 217.12 | 217.12 | 0 | 217.12 | 0 | 1 | 226.02 | 226.02 | 0 | 0 | 0 | 1 | 1 | 217.12 | 217.12
129 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Plain Bend 75 mm | NOS | 2 | 43.87 | 87.74 | 2 | 43.87 | 87.74 | 0 | 43.87 | 0 | 2 | 55.77 | 111.53 | 0 | 0 | 0 | 2 | 2 | 87.74 | 87.74
130 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Plain Tee 75 mm | NOS | 2 | 60.57 | 121.14 | 2 | 60.57 | 121.14 | 0 | 60.57 | 0 | 2 | 72.69 | 145.38 | 0 | 0 | 0 | 2 | 2 | 121.14 | 121.14
131 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Plug Bend 75 mm | NOS | 3 | 90.86 | 272.58 | 3 | 90.86 | 272.58 | 0 | 90.86 | 0 | 3 | 68.91 | 206.7399 | 0 | 0 | 0 | 3 | 3 | 272.58 | 272.58
132 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)SWR Shoe Bend 75mm | NOS | 2 | 39.69 | 79.38 | 2 | 39.69 | 79.38 | 0 | 39.69 | 0 | 2 | 43.42 | 86.84 | 0 | 0 | 0 | 2 | 2 | 79.38 | 79.38
133 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)Teflon Tape | NOS | 14 | 23.6 | 330.4 | 14 | 23.6 | 330.4 | 1 | 23.6 | 23.6 | 14 | 24.02 | 336.22 | 0 | 0 | 0 | 13 | 14 | 306.8 | 330.4
134 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC 2" Brass MTA | NOS | 1 | 496.86 | 496.86 | 1 | 496.86 | 496.86 | 0 | 496.86 | 0 | 1 | 531.19 | 531.19 | 0 | 0 | 0 | 1 | 1 | 496.86 | 496.86
135 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Ball Valves 1" | NOS | 1 | 190.58 | 190.58 | 1 | 190.58 | 190.58 | 0 | 190.58 | 0 | 1 | 148.9 | 148.9 | 0 | 0 | 0 | 1 | 1 | 190.58 | 190.58
136 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Ball Valves 1/2" | NOS | 5 | 59.48 | 297.4 | 5 | 59.48 | 297.4 | 1 | 59.48 | 59.48 | 5 | 89.15 | 445.77 | 0 | 0 | 0 | 4 | 5 | 237.92 | 297.4
137 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Brass FTA 1" | NOS | 1 | 116.14 | 116.14 | 1 | 116.14 | 116.14 | 0 | 116.14 | 0 | 1 | 120.9 | 120.9 | 0 | 0 | 0 | 1 | 1 | 116.14 | 116.14
138 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Elbow 1" (45 degree) | NOS | 10 | 18.88 | 188.8 | 10 | 18.88 | 188.8 | 1 | 18.88 | 18.88 | 10 | 19.16 | 191.58 | 0 | 0 | 0 | 9 | 10 | 169.92 | 188.8
139 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Elbow 1" (90 degree) | NOS | 4 | 17.46 | 69.84 | 4 | 17.46 | 69.84 | 0 | 17.46 | 0 | 4 | 19.65 | 78.6 | 0 | 0 | 0 | 4 | 4 | 69.84 | 69.84
140 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Elbow 1/2" (90 degree) | NOS | 3 | 10.5 | 31.5 | 3 | 10.5 | 31.5 | 0 | 10.5 | 0 | 3 | 8.84 | 26.5299 | 0 | 0 | 0 | 3 | 3 | 31.5 | 31.5
141 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Elbow 2" (90 degree) | NOS | 7 | 55.88 | 391.16 | 7 | 55.88 | 391.16 | 1 | 55.88 | 55.88 | 7 | 60.32 | 422.2502 | 0 | 0 | 0 | 6 | 7 | 335.28 | 391.16
142 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC End Cap 2" | NOS | 1 | 80.24 | 80.24 | 1 | 80.24 | 80.24 | 0 | 80.24 | 0 | 1 | 31.75 | 31.75 | 0 | 0 | 0 | 1 | 1 | 80.24 | 80.24
143 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Pipe 1" X 3m long (SHD-40) | NOS | 20 | 218.73 | 4374.6 | 20 | 218.73 | 4374.6 | 2 | 218.73 | 437.46 | 20 | 246.95 | 4938.9407 | 0 | 0 | 0 | 18 | 20 | 3937.14 | 4374.6
144 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Pipe 1/2" X 3m long (SHD-40) | NOS | 1 | 136.22 | 136.22 | 1 | 136.22 | 136.22 | 0 | 136.22 | 0 | 1 | 116.69 | 116.69 | 0 | 0 | 0 | 1 | 1 | 136.22 | 136.22
145 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Pipe 2" X 3m long (SHD-40) | NOS | 2 | 1257.88 | 2515.76 | 2 | 1257.88 | 2515.76 | 0 | 1257.88 | 0 | 2 | 497.58 | 995.16 | 0 | 0 | 0 | 2 | 2 | 2515.76 | 2515.76
146 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Solvent 237ml | NOS | 2 | 202.87 | 405.74 | 2 | 202.87 | 405.74 | 0 | 202.87 | 0 | 2 | 193.28 | 386.56 | 0 | 0 | 0 | 2 | 2 | 405.74 | 405.74
147 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Tee 1"x1/2" | NOS | 1 | 23.12 | 23.12 | 1 | 23.12 | 23.12 | 0 | 23.12 | 0 | 1 | 24.07 | 24.07 | 0 | 0 | 0 | 1 | 1 | 23.12 | 23.12
148 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Tee 2" | NOS | 4 | 109.79 | 439.16 | 4 | 109.79 | 439.16 | 0 | 109.79 | 0 | 4 | 81.9 | 327.6001 | 0 | 0 | 0 | 4 | 4 | 439.16 | 439.16
149 | Plumbing Swimming Pool Plumbing work | 10 | Started | Material | (M)UPVC Tee 2"x1/2" | NOS | 1 | 65.92 | 65.92 | 1 | 65.92 | 65.92 | 0 | 65.92 | 0 | 1 | 68.62 | 68.62 | 0 | 0 | 0 | 1 | 1 | 65.92 | 65.92
150 | Plumbing Swimming pool Plumbing M+L | 0 | Started | Labour | (L)Swimming Pool Plumbing M+L | lumsum | 1 | 335120 | 335120 | 0 | 0 | 0 | 0 | 335120 | 0 | 1 | 335120 | 335120 | 1 | 335120 | 335120 | 1 | 0 | 335120 | 0
151 | Plumbing Swimming pool Plumbing M+L | 0 | Started | Labour | (L)Water Fall for Swimming Pool Labour | lumsum | 1 | 29438.64 | 29438.64 | 0 | 0 | 0 | 0 | 29438.64 | 0 | 1 | 29438.64 | 29438.64 | 1 | 29438.64 | 29438.64 | 1 | 0 | 29438.64 | 0
152 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)10 sq.mm x 4 core Aluminium Armoured Cable | RMT | 55 | 130.01 | 7150.55 | 55 | 130.01 | 7150.55 | 6 | 130.01 | 780.06 | 55 | 130 | 7150.0275 | 0 | 0 | 0 | 49 | 55 | 6370.49 | 7150.55
153 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)12M Plate 910012 | PCS | 1 | 141.6 | 141.6 | 1 | 141.6 | 141.6 | 0 | 141.6 | 0 | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 1 | 1 | 141.6 | 141.6
154 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)12M S/F Box | NOS | 1 | 82.6 | 82.6 | 1 | 82.6 | 82.6 | 0 | 82.6 | 0 | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
155 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)12W Garden spike | NOS | 3 | 1156.4 | 3469.2 | 3 | 1156.4 | 3469.2 | 0 | 1156.4 | 0 | 3 | 1156.4 | 3469.2 | 0 | 0 | 0 | 3 | 3 | 3469.2 | 3469.2
156 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)1M 16A Switch 900052 | PCS | 3 | 64.9 | 194.7 | 3 | 64.9 | 194.7 | 0 | 64.9 | 0 | 3 | 64.9 | 194.7 | 0 | 0 | 0 | 3 | 3 | 194.7 | 194.7
157 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)20A - 2 way AC Box | NOS | 5 | 1947 | 9735 | 5 | 1947 | 9735 | 1 | 1947 | 1947 | 5 | 1947 | 9735 | 0 | 0 | 0 | 4 | 5 | 7788 | 9735
158 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)20W LED Batten | NOS | 1 | 212.4 | 212.4 | 1 | 212.4 | 212.4 | 0 | 212.4 | 0 | 1 | 212.4 | 212.4 | 0 | 0 | 0 | 1 | 1 | 212.4 | 212.4
159 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)2M 16A Socket 900057 | NOS | 3 | 94.4 | 283.2 | 3 | 94.4 | 283.2 | 0 | 94.4 | 0 | 3 | 94.4 | 283.2 | 0 | 0 | 0 | 3 | 3 | 283.2 | 283.2
160 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)32A 4P MCB GM VFC 32-NA | NOS | 2 | 960 | 1920 | 2 | 960 | 1920 | 0 | 960 | 0 | 2 | 960 | 1920 | 0 | 0 | 0 | 2 | 2 | 1920 | 1920
161 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)32X6 Screw | NOS | 24 | 1.47 | 35.28 | 24 | 1.47 | 35.28 | 2 | 1.47 | 2.94 | 24 | 1.48 | 35.4 | 0 | 0 | 0 | 22 | 24 | 32.34 | 35.28
162 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)35x8 RP PVC | NOS | 1 | 17.7 | 17.7 | 1 | 17.7 | 17.7 | 0 | 17.7 | 0 | 1 | 17.7 | 17.7 | 0 | 0 | 0 | 1 | 1 | 17.7 | 17.7
163 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)3W Wave Panel | NOS | 5 | 212.4 | 1062 | 5 | 212.4 | 1062 | 1 | 212.4 | 212.4 | 5 | 212.4 | 1062 | 0 | 0 | 0 | 4 | 5 | 849.6 | 1062
164 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)4 Poll MCB M/S Box | NOS | 2 | 188.8 | 377.6 | 2 | 188.8 | 377.6 | 0 | 188.8 | 0 | 2 | 165.2 | 330.4 | 0 | 0 | 0 | 2 | 2 | 377.6 | 377.6
165 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)4M Foot Lamp | NOS | 4 | 1121 | 4484 | 4 | 1121 | 4484 | 0 | 1121 | 0 | 4 | 1121 | 4484 | 0 | 0 | 0 | 4 | 4 | 4484 | 4484
166 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)5W Garden Spike | NOS | 20 | 649 | 12980 | 20 | 649 | 12980 | 2 | 649 | 1298 | 20 | 649 | 12980 | 0 | 0 | 0 | 18 | 20 | 11682 | 12980
167 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)6A 3Pin Socket 900061 | NOS | 1 | 33.04 | 33.04 | 1 | 33.04 | 33.04 | 0 | 33.04 | 0 | 1 | 33.04 | 33.04 | 0 | 0 | 0 | 1 | 1 | 33.04 | 33.04
168 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)6A Switch 1M 900001 | NOS | 7 | 16.52 | 115.64 | 7 | 16.52 | 115.64 | 1 | 16.52 | 16.52 | 7 | 16.52 | 115.64 | 0 | 0 | 0 | 6 | 7 | 99.12 | 115.64
169 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)6M Plate 910006 | NOS | 1 | 82.6 | 82.6 | 1 | 82.6 | 82.6 | 0 | 82.6 | 0 | 1 | 82.6 | 82.6 | 0 | 0 | 0 | 1 | 1 | 82.6 | 82.6
170 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)6M S/F Box | NOS | 1 | 59 | 59 | 1 | 59 | 59 | 0 | 59 | 0 | 1 | 59 | 59 | 0 | 0 | 0 | 1 | 1 | 59 | 59
171 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)Flexible Cable 1 sq.mm x 1 core | RMT | 200 | 1 | 200 | 200 | 1 | 200 | 20 | 1 | 20 | 200 | 12.27 | 2454.4 | 0 | 0 | 0 | 180 | 200 | 180 | 200
172 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)Flexible Cable 1 sq.mm x 4 core | RMT | 40 | 1 | 40 | 40 | 1 | 40 | 4 | 1 | 4 | 40 | 64.9 | 2596 | 0 | 0 | 0 | 36 | 40 | 36 | 40
173 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)Flexible Cable 1.5 sq.mm x 2 core | RMT | 50 | 49.56 | 2478 | 50 | 49.56 | 2478 | 5 | 49.56 | 247.8 | 50 | 42 | 2099.82 | 0 | 0 | 0 | 45 | 50 | 2230.2 | 2478
174 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)LED Stricker 3W | PCS | 4 | 141.6 | 566.4 | 4 | 141.6 | 566.4 | 0 | 141.6 | 0 | 4 | 141.6 | 566.4 | 0 | 0 | 0 | 4 | 4 | 566.4 | 566.4
175 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)LED Wall Light 2x3 Watt | NOS | 7 | 679.99 | 4759.93 | 7 | 679.99 | 4759.93 | 1 | 679.99 | 679.99 | 7 | 680 | 4759.9902 | 0 | 0 | 0 | 6 | 7 | 4079.94 | 4759.93
176 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)PVC Casing Patti 1"" | NOS | 2 | 50.74 | 101.48 | 2 | 50.74 | 101.48 | 0 | 50.74 | 0 | 2 | 50.74 | 101.48 | 0 | 0 | 0 | 2 | 2 | 101.48 | 101.48
177 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)Steel Grip PVC Tape | NOS | 5 | 11.8 | 59 | 5 | 11.8 | 59 | 1 | 11.8 | 11.8 | 5 | 11.8 | 59 | 0 | 0 | 0 | 4 | 5 | 47.2 | 59
178 | Electrical Swimming Pool Electrical Work | 10 | Started | Material | (M)Waterproof Tape | NOS | 5 | 23.6 | 118 | 5 | 23.6 | 118 | 1 | 23.6 | 23.6 | 5 | 23.6 | 118 | 0 | 0 | 0 | 4 | 5 | 94.4 | 118
179 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Aldrop | SET | 2 | 90 | 180 | 2 | 90 | 180 | 0 | 90 | 0 | 2 | 70.8 | 141.6 | 0 | 0 | 0 | 2 | 2 | 180 | 180
180 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Hinges 2" | PCS | 2 | 60 | 120 | 2 | 60 | 120 | 0 | 60 | 0 | 2 | 70.8 | 141.6 | 0 | 0 | 0 | 2 | 2 | 120 | 120
181 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Hinges 3" | NOS | 8 | 20 | 160 | 8 | 20 | 160 | 1 | 20 | 20 | 8 | 103.3 | 826.4 | 0 | 0 | 0 | 7 | 8 | 140 | 160
182 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Instruction Board | NOS | 1 | 1800 | 1800 | 1 | 1800 | 1800 | 0 | 1800 | 0 | 1 | 1800 | 1800 | 0 | 0 | 0 | 1 | 1 | 1800 | 1800
183 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Medium Lock | NOS | 1 | 95 | 95 | 1 | 95 | 95 | 0 | 95 | 0 | 1 | 47.2 | 47.2 | 0 | 0 | 0 | 1 | 1 | 95 | 95
184 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Material | (M)Square Plate 4x4 | NOS | 2 | 35 | 70 | 2 | 35 | 70 | 0 | 35 | 0 | 2 | 35 | 70 | 0 | 0 | 0 | 2 | 2 | 70 | 70
185 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Labour | (L)Helper | NOS | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | 700 | 700 | 1 | 700 | 700 | 1 | 0 | 700 | 0
186 | Entry Gate Swimming Pool Entry Gate | 10 | Started | Labour | (L)Welder | NOS | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 1 | 0 | 1200 | 0
187 | Swimming pool Railing fabrication | 0 | Started | Labour | (L)Eurolight for pipe fixing | lumsum | 1 | 320 | 320 | 0 | 0 | 0 | 0 | 320 | 0 | 1 | 320 | 320 | 1 | 320 | 320 | 1 | 0 | 320 | 0
188 | Swimming pool Railing fabrication | 0 | Started | Labour | (L)Pipe bending labour | lumsum | 1 | 700 | 700 | 0 | 0 | 0 | 0 | 700 | 0 | 1 | 700 | 700 | 1 | 700 | 700 | 1 | 0 | 700 | 0
189 | Swimming pool Railing fabrication | 0 | Started | Labour | (L)Swimming pool Railing | SQFT | 186 | 40 | 7440 | 0 | 0 | 0 | 0 | 40 | 0 | 186 | 40 | 7440 | 186 | 40 | 7440 | 186 | 0 | 7440 | 0
190 | Swimming Pool Swimming Pool Pergola | 0 | Started | Material | (M)4" Roller | NOS | 1 | 70 | 70 | 1 | 70 | 70 | 0 | 70 | 0 | 1 | 70 | 70 | 0 | 0 | 0 | 1 | 1 | 70 | 70
191 | Swimming Pool Swimming Pool Pergola | 0 | Started | Material | (M)Thinner | LITRE | 2 | 120 | 240 | 2 | 120 | 240 | 0 | 120 | 0 | 2 | 120 | 240 | 0 | 0 | 0 | 2 | 2 | 240 | 240
192 | Swimming Pool Swimming Pool Pergola | 0 | Started | Labour | (L)Helper | NOS | 6 | 700 | 4200 | 0 | 0 | 0 | 0 | 700 | 0 | 6 | 700 | 4200 | 6 | 700 | 4200 | 6 | 0 | 4200 | 0
193 | Swimming Pool Swimming Pool Pergola | 0 | Started | Labour | (L)Welder | NOS | 6 | 1200 | 7200 | 0 | 0 | 0 | 0 | 1200 | 0 | 6 | 1200 | 7200 | 6 | 1200 | 7200 | 6 | 0 | 7200 | 0
194 | Swimming Pool Core Cutting | 10 | Started | Labour | (L)Core Cutting | PER INCH | 67 | 75 | 5025 | 0 | 0 | 0 | 7 | 75 | 525 | 67 | 75 | 5025 | 67 | 75 | 5025 | 60 | 0 | 4500 | 0
195 | Swimming Pool Labours only | 0 | Started | Labour | (L)Swimming pool labours | LITRE | 67354 | 6.79 | 457333.66 | 0 | 0 | 0 | 0 | 6.79 | 0 | 67354 | 6.79 | 456996.9 | 67354 | 6.79 | 456996.9 | 67354 | 0 | 457333.66 | 336.76
196 | Swimming pool Department labours | 0 | Started | Labour | (L)F/C | NOS | 4 | 649 | 2596 | 0 | 0 | 0 | 0 | 649 | 0 | 4 | 649 | 2596 | 4 | 649 | 2596 | 4 | 0 | 2596 | 0
197 | Swimming pool Department labours | 0 | Started | Labour | (L)M/C | NOS | 35 | 826 | 28910 | 0 | 0 | 0 | 0 | 826 | 0 | 35 | 826 | 28910 | 35 | 826 | 28910 | 35 | 0 | 28910 | 0
198 | Swimming pool Department labours | 0 | Started | Labour | (L)Mason | NOS | 2 | 1180 | 2360 | 0 | 0 | 0 | 0 | 1180 | 0 | 2 | 1180 | 2360 | 2 | 1180 | 2360 | 2 | 0 | 2360 | 0
199 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Areca palm (5Ft) M+L | NOS | 20 | 400 | 8000 | 0 | 0 | 0 | 0 | 400 | 0 | 20 | 400 | 8000 | 20 | 400 | 8000 | 20 | 0 | 8000 | 0
200 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Cristina Ficus (2Ft) M+L | NOS | 20 | 100 | 2000 | 0 | 0 | 0 | 0 | 100 | 0 | 20 | 100 | 2000 | 20 | 100 | 2000 | 20 | 0 | 2000 | 0
201 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Dracaena Mahatma (2Ft) M+L | NOS | 25 | 40 | 1000 | 0 | 0 | 0 | 0 | 40 | 0 | 25 | 40 | 1000 | 25 | 40 | 1000 | 25 | 0 | 1000 | 0
202 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Fertilizer M+L | KG | 100 | 20 | 2000 | 0 | 0 | 0 | 0 | 20 | 0 | 100 | 20 | 2000 | 100 | 20 | 2000 | 100 | 0 | 2000 | 0
203 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Fountain Grass (2Ft) M+L | NOS | 20 | 50 | 1000 | 0 | 0 | 0 | 0 | 50 | 0 | 20 | 50 | 1000 | 20 | 50 | 1000 | 20 | 0 | 1000 | 0
204 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Heliconia (2Ft) M+L | NOS | 20 | 80 | 1600 | 0 | 0 | 0 | 0 | 80 | 0 | 20 | 80 | 1600 | 20 | 80 | 1600 | 20 | 0 | 1600 | 0
205 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Heliconia rostrata (2Ft) M+L | NOS | 40 | 150 | 6000 | 0 | 0 | 0 | 0 | 150 | 0 | 40 | 150 | 6000 | 40 | 150 | 6000 | 40 | 0 | 6000 | 0
206 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Madhumalti M+L | NOS | 6 | 60 | 360 | 0 | 0 | 0 | 0 | 60 | 0 | 6 | 60 | 360 | 6 | 60 | 360 | 6 | 0 | 360 | 0
207 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Morning Glory M+L | NOS | 3 | 30 | 90 | 0 | 0 | 0 | 0 | 30 | 0 | 3 | 30 | 90 | 3 | 30 | 90 | 3 | 0 | 90 | 0
208 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Nursary Labours only | LUMPSUM | 1 | 11000 | 11000 | 0 | 0 | 0 | 0 | 11000 | 0 | 1 | 11000 | 11000 | 1 | 11000 | 11000 | 1 | 0 | 11000 | 0
209 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Russelia Red M+L | NOS | 60 | 35 | 2100 | 0 | 0 | 0 | 0 | 35 | 0 | 60 | 35 | 2100 | 60 | 35 | 2100 | 60 | 0 | 2100 | 0
210 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Singapuri Chafa (5Ft) M+L | NOS | 6 | 2000 | 12000 | 0 | 0 | 0 | 0 | 2000 | 0 | 6 | 2000 | 12000 | 6 | 2000 | 12000 | 6 | 0 | 12000 | 0
211 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Soil M+L | BRASS | 3 | 1500 | 4500 | 0 | 0 | 0 | 0 | 1500 | 0 | 3 | 1500 | 4500 | 3 | 1500 | 4500 | 3 | 0 | 4500 | 0
212 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Transport | TRIP | 1 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 1 | 3000 | 3000 | 1 | 3000 | 3000 | 1 | 0 | 3000 | 0
213 | Swimming Pool Garden M+L | 0 | Started | Labour | (L)Vavigated Canna (2Ft) M+L | NOS | 20 | 50 | 1000 | 0 | 0 | 0 | 0 | 50 | 0 | 20 | 50 | 1000 | 20 | 50 | 1000 | 20 | 0 | 1000 | 0
214 | Swimming Pool Green net Pole Labours | 100 |  | Labour | (L)Helper | NOS | 2 | 700 | 1400 | 0 | 0 | 0 | 2 | 700 | 1400 | 2 | 700 | 1400 | 2 | 700 | 1400 | 0 | 0 | 0 | 0
215 | Swimming Pool Green net Pole Labours | 100 |  | Labour | (L)Welder | NOS | 1 | 1200 | 1200 | 0 | 0 | 0 | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 0 | 0 | 0 | 0
216 | Maintenance SP Maintenance from 4th march to 3rd Apr | 0 | Started | Labour | (L)Maintenance Charges | lumsum | 1 | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 0 | 1 | 7500 | 7500 | 1 | 7500 | 7500 | 1 | 0 | 7500 | 0
217 | Painting Swimming Pool Painting | 0 | Started | Labour | (L)OBD Paint M+L | SQFT | 82.9596 | 9.44 | 783.14 | 0 | 0 | 0 | 0 | 9.44 | 0 | 82.9596 | 10.62 | 881.0364 | 82.9596 | 10.62 | 881.04 | 82.9596 | 0 | 783.139 | -97.9014
218 | Painting Swimming Pool Painting | 0 | Started | Labour | (L)Oil Paint Material+Labour | SQFT | 194.541 | 10.62 | 2066.03 | 0 | 0 | 0 | 0 | 10.62 | 0 | 194.541 | 10.62 | 2066.029 | 194.541 | 10.62 | 2066.03 | 194.541 | 0 | 2066.025 | -0.0046
219 | Painting Swimming Pool Painting | 0 | Started | Labour | (L)Texture Paint M+L | SQFT | 697.4632 | 35.4 | 24690.2 | 0 | 0 | 0 | 0 | 35.4 | 0 | 697.4632 | 36.58 | 25513.1992 | 697.4632 | 36.58 | 25513.2 | 697.4632 | 0 | 24690.197 | -823.0027
220 | Pump Room Painting | 0 | Started | Labour | (L)Apex Paint M+L | SQFT | 210.248 | 11.8 | 2480.93 | 0 | 0 | 0 | 0 | 11.8 | 0 | 210.248 | 12.98 | 2729.028 | 210.248 | 12.98 | 2729.03 | 210.248 | 0 | 2480.926 | -248.1036
221 | Pump Room Painting | 0 | Started | Labour | (L)OBD Paint M+L | SQFT | 159.463 | 9.44 | 1505.33 | 0 | 0 | 0 | 0 | 9.44 | 0 | 159.463 | 10.62 | 1693.507 | 159.463 | 10.62 | 1693.51 | 159.463 | 0 | 1505.331 | -188.1793