## Project_Work_Order6385551319554
Project Work Order
From 04 Jan 2024 To 03 Jul 2024
Page 1 of 1
Total Records: 145 Records 1 To 145
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 4 | 68316.94 | 273267.76 | 49188.2 | 322455.96 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 1.5BHK electrical work M+L | NOS | 3 | 68316.94 | 204950.82 | 36891.14 | 241841.96 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 4 | 49706.77 | 198827.08 | 35788.88 | 234615.96 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 8 | 49706.77 | 397654.16 | 71577.74 | 469231.9 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 1 | 49706.77 | 49706.77 | 8947.22 | 58653.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 1BHK electrical work M+L | NOS | 2 | 49706.77 | 99413.54 | 17894.44 | 117307.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 2 | 72411.01 | 144822.02 | 26067.96 | 170889.98 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 2.5BHK electrical work M+L | NOS | 1 | 72411.01 | 72411.01 | 13033.98 | 85444.99 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 1 | 69868.64 | 69868.64 | 12576.36 | 82445 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 1 | 69868.64 | 69868.64 | 12576.36 | 82445 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 8th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 7th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 13th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 12th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 11th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 10th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 9th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 15th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 3 | 69868.64 | 209605.92 | 37729.06 | 247334.98 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 6th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 5th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 4th Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 3rd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 2nd Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 1st Floor Internal Electrical work | 2BHK electrical work M+L | NOS | 2 | 69868.64 | 139737.28 | 25152.72 | 164890 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | C-Bldg LT works & Motion Sensor LED lights in floor lobby & | Electrical Work M+L | NOS | 1391002 | 1 | 1391002 | 250380.36 | 1641382.36 | 5 | 0 | 0 | 0 | 0 | 1391002 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | E-Bldg Electric Car Charging Bay | Electrical Work M+L | NOS | 755669 | 1 | 755669 | 136020.42 | 891689.42 | 5 | 0 | 0 | 0 | 0 | 755669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | D-Bldg Electric Car Charging Bay | Electrical Work M+L | NOS | 755669 | 1 | 755669 | 136020.42 | 891689.42 | 5 | 0 | 0 | 0 | 0 | 755669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | C-Bldg Electric Car Charging Bay | Electrical Work M+L | NOS | 755669 | 1 | 755669 | 136020.42 | 891689.42 | 5 | 0 | 0 | 0 | 0 | 755669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | E-Bldg Lightning arresters, earthing etc. | Electrical Work M+L | NOS | 132669 | 1 | 132669 | 23880.42 | 156549.42 | 5 | 0 | 0 | 0 | 0 | 132669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | D-Bldg Lightning arresters, earthing etc. | Electrical Work M+L | NOS | 132669 | 1 | 132669 | 23880.42 | 156549.42 | 5 | 0 | 0 | 0 | 0 | 132669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | C-Bldg Lightning arresters, earthing etc. | Electrical Work M+L | NOS | 132669 | 1 | 132669 | 23880.42 | 156549.42 | 5 | 0 | 0 | 0 | 0 | 132669 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | E-Bldg Street lights with CFL Fittings | Electrical Work M+L | NOS | 145169 | 1 | 145169 | 26130.42 | 171299.42 | 5 | 0 | 0 | 0 | 0 | 145169 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | D-Bldg Street lights with CFL Fittings | Electrical Work M+L | NOS | 145169 | 1 | 145169 | 26130.42 | 171299.42 | 5 | 0 | 0 | 0 | 0 | 145169 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | C-Bldg Street lights with CFL Fittings | Electrical Work M+L | NOS | 145169 | 1 | 145169 | 26130.42 | 171299.42 | 5 | 0 | 0 | 0 | 0 | 145169 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | Electrical for parking slabs | Parking Slab Electrical M+L | NOS | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Cancelled | SakshiB | 01 Jul 2024 | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | Electrical for parking slabs | Parking Slab Electrical M+L | NOS | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Cancelled | SakshiB | 01 Jul 2024 | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | Electrical for parking slabs | Parking Slab Electrical M+L | NOS | 0 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Cancelled | SakshiB | 01 Jul 2024 | 0
Adhya Radhakrishna | 53 | 0 | 01 Jun 2023 | J J Electricals | 14th Floor Internal Electrical work | 3BHK electrical work M+L | NOS | 1 | 72411.02 | 72411.02 | 13033.98 | 85445 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  | SakshiB |  | construction |  |  |  | Un-Approved |  |  | 0